🧩 1. FUNCTION POINT (FP) ESTIMATION

The Function Point method estimates software size by measuring the functionality delivered to the user, independent of programming language or technology.

🧱 Step 1: Identify System Components

| Component Type | Description | Count | Weight (Average) | FP Count |
| --- | --- | --- | --- | --- |
| External Inputs (EI) | Add/Update/Delete book, member, issue records | 8 | 4 | 32 |
| External Outputs (EO) | Reports (issued books, overdue, recommendations) | 5 | 5 | 25 |
| External Inquiries (EQ) | Search books, query recommendations | 4 | 4 | 16 |
| Internal Logical Files (ILF) | Book file, Member file, Transaction file | 3 | 10 | 30 |
| External Interface Files (EIF) | External databases (e.g., eBook source) | 1 | 7 | 7 |

Unadjusted Function Points (UFP) = 32 + 25 + 16 + 30 + 7 = 110

⚙️ Step 2: Compute Value Adjustment Factor (VAF)

There are 14 general system characteristics, each rated from 0 (no influence) to 5 (strong influence).

| Factor | Description | Rating |
| --- | --- | --- |
| Data communications | 3 |  |
| Distributed processing | 2 |  |
| Performance | 3 |  |
| Heavily used configuration | 2 |  |
| Transaction rate | 3 |  |
| Online data entry | 4 |  |
| End-user efficiency | 4 |  |
| Online update | 4 |  |
| Complex processing | 4 |  |
| Reusability | 3 |  |
| Installation ease | 2 |  |
| Operational ease | 3 |  |
| Multiple sites | 1 |  |
| Facilitate change | 3 |  |

Total = 41

VAF=0.65+(0.01×41)=1.06

📊 Step 3: Compute Adjusted Function Points (AFP)

AFP=UFP×VAF=110×1.06=116.6≈117

✅ Final Adjusted Function Points = 117

🧮 2. COCOMO ESTIMATION

We’ll use the Basic COCOMO (Constructive Cost Model) to estimate effort, development time, and staffing.

Step 1: Determine the Project Type

Your project is a “Semi-Detached” type:

- Medium complexity

- Experience level moderate

- Mix of algorithms and database work

Step 2: Estimate KLOC (Thousand Lines of Code)

Typically, 1 FP ≈ 50 LOC (for Python projects)

117 FP×50=5850 LOC=5.85 KLOC

Step 3: Apply Basic COCOMO Equations

For Semi-Detached:

Effort (E)=3.0×(KLOC)1.12
Development Time (D)=2.5×(Effort)0.35
People Required (P)=EffortDevelopment Time

Calculate Effort:

E=3.0×(5.85)1.12=3.0×7.02=21.06 person-months

Calculate Development Time:

D=2.5×(21.06)0.35=2.5×2.73=6.83 months

Calculate Average Staff Size:

P=21.066.83=3.08≈3 persons

✅ Effort = 21.06 person-months
✅ Duration = 6.8 months
✅ Team = 3 people

Step 4: Estimated Cost

Assume cost per person-month = ₹50,000 (academic scale)

Total Cost=21.06×50,000=₹10,53,000

✅ Estimated Project Cost = ₹10.53 Lakhs

🗓️ 3. PROJECT SCHEDULE (Gantt-Style)

Project Duration ≈ 7 months
Team Size = 3 members (Analyst, Developer, Tester)

| Phase | Activities | Duration (weeks) | Deliverables |
| --- | --- | --- | --- |
| 1. Requirement Analysis | Gather requirements, SRS, feasibility study | 2 | SRS Document |
| 2. System Design | DFD, UML, Database Schema, Architecture | 3 | Design Document |
| 3. Algorithm Design & Testing | Implement A*, Hill Climbing, Graph Search | 3 | Algorithm modules |
| 4. Implementation | Develop modules (Book Mgmt, User Mgmt, Search) | 6 | Functional LMS |
| 5. Integration & Testing | Unit + Integration + User testing | 3 | Tested System |
| 6. Deployment | Install system, final checks | 2 | Working LMS |
| 7. Documentation & Training | User manual, technical documentation | 2 | Final Report |

Total Duration = ~21 Weeks (≈ 5.25 months)
(Some overlap expected → ~6–7 months total timeline)

📊 Summary Table

| Parameter | Value |
| --- | --- |
| Function Points (FP) | 117 |
| KLOC | 5.85 |
| COCOMO Effort | 21.06 person-months |
| Development Time | 6.8 months |
| Team Size | 3 |
| Estimated Cost | ₹10.53 Lakhs |
| Schedule Duration | 21 weeks |